## DPR 25-Sep
NE Electricals & Instruments / Brahmaputra Civil Works — Daily Progress Report
Project: RFX Assam |  | Date: 25/09/2026
Sl | Desc of Work | Area / Locn | Qty Done | Nos | Manpwr | Remarks
1 | Cable pulling tray T-5 | Unit 2 Rack A | 180 | m | 10 | continued
2 | Cable tray installation tray T-6 | Unit 2 Rack A | 24 | m | 6 | in progress
3 | LT panel erection | SS-2 | 2 | nos | 5 | completed
4 | Cable termination HT panel | SS-2 | 12 | nos | 4 | started
5 | Loop check L-305 | Pump House | 1 | nos | 2 | done
6 | Impulse tubing | Pump House | 30 | m | 3 | in progress
7 | Excavation F-14 | Unit 3 Fdn area | 45 | m3 | 8 | started
8 | Reinforcement F-13 | Unit 3 Fdn area | 1.2 | MT | 6 | in progress
9 | Basin wall waterproofing | Cooling Tower | 40 | sqm | 5 | started
10 | Tank pad sand filling | Tank Farm | 60 | m3 | 7 | completed
11 | Motor cabling P-101A/B | Pump House | 90 | m | 4 | in progress
12 | Instrument cable tray | Rack C | 18 | m | 3 | continued